## AgilePM products
|  |  | AgilePM products | Anybody | Solution Participants Users | Project Governance Authority | Business Sponsor | Business Visionary | Technical Co-ordinator | Project Manager | Business Analyst | Team Leader | Solutions Developers | Solutions Testers | Business Ambassador | Technical Advisor | Business Advisor | Workshop Facilitator | Agile/DSDM Coach
| Type |  |  | Other |  |  | Project level |  |  |  | Solutions Development Team |  |  |  |  | Supporting
| G = Gate |  | Key | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
| Ev = Evolutionary |  | B - Produced by
F - Produced for
Product Category | Type |  | A - Approved by
|  | PHASE | Pre-project
Business | G |  | Terms of Reference (ToR) | B |  | B | A |  | F |  | F
|  | PHASE | Feasibility
Business | Ev |  | Business Case |  |  | F | A |  |  |  | B
Business | Ev |  | Prioritised Requirements List (PRL) | F |  |  |  | A |  |  | B
Solution | Ev |  | Solution Architecture Definition |  |  |  |  | A | B | A | B | F | F | F | F
Solution | Ev |  | Development Approach Definition | [5 empty] | B | A | F | F | F | F | F
Management | G |  | Feasibility Assessment |  |  | F | A |  |  | B
Management | Ev |  | Delivery Plan | F |  |  |  | A | A | B
Management | Ev |  | Management Approach Definition |  |  | F | A |  |  | B
|  | PHASE | Foundations
Management | G |  | Foundation Summary |  |  | F | A |  |  | B
|  | PHASE | Evolutionary Development
Management | Ev |  | Evolving Solution |  | F |  | F | A | A |  | B | B | B | B | B
Management | Ev |  | Timebox Plan | [6 empty] | A | B/F | B/F | B/F | B/F | B/F
Management | G |  | Timebox Review Record |  |  | F |  | A | A |  |  | B
|  | PHASE | Deployment
Management | G |  | Project Review Report | F |  |  |  | A | A | B |  | A
|  | PHASE | Post-project
Business | G |  | Benefits Assessment |  |  | F | A | B |  |  | B
[7 empty] | Sponsor | Cliente | [6 empty] | User
[8 empty] | Macro-Requisiti | [6 empty] | Details
[8 empty] | Epic | [6 empty] | User-stories